## Sheet1
Liquid Propellent Engine Test Stand Integration and Testing ■ Completed ■ Elapsed ■ Remaining | 2019-01-06 | 2019-01-13 | 2019-01-20 | 2019-01-27 | 2019-02-03 | 2019-02-10 | 2019-02-17 | 2019-02-24 | 2019-03-03 | 2019-03-10 | 2019-03-17 | 2019-03-24 | 2019-03-31 | 2019-04-07 | 2019-04-14 | 2019-04-21 | 2019-04-28 | 2019-05-05 | 2019-05-12 | 2019-05-19 | 2019-05-26 | 2019-06-02 | 2019-06-09
Pintle Test
Water Test Pintle V1 | bar: 2019-01-06 to 2019-02-03
Analysis of Pintle V1 Test | bar: 2019-01-20 to 2019-02-10
Design Pintle V2 | bar: 2019-02-10 to 2019-03-17
Manufacture Pintle V2 | bar: 2019-03-17 to 2019-03-31
Water Test Pintle V2 | 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0
TEST STAND
CAD
Pressure Section | bar: 2019-02-17 to 2019-03-17
IPA Section | bar: 2019-02-17 to 2019-03-17
LOX Section | bar: 2019-02-17 to 2019-03-17
HARDWARE
Pressure Section Ordered | bar: 2019-03-03 to 2019-03-24
IPA Section Ordered | bar: 2019-03-03 to 2019-03-24
lox Section Ordered | bar: 2019-03-03 to 2019-03-24
Pressure Section Installed | 2019-03-10: 1; 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0
IPA Section Construction | 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0
lox Section Construction | 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0; 2019-05-05: 0; 2019-05-12: 0
MAIN FUEL/LOX VALVE
Cryogenic conditions valve torque test | bar: 2019-01-06 to 2019-02-17
Valve actuator design review & Parts Order | bar: 2019-02-10 to 2019-03-03
Build custom bracket | 2019-02-24: 1; 2019-03-03: 1; 2019-03-10: 1; 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0
IGNITER
Spark Torch Igniter Proof-of Concept | bar: 2019-01-06 to 2019-02-17
External Igniter Design | bar: 2019-03-03 to 2019-03-31
External Igniter Prototype | 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0
External Igniter Installed | 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0; 2019-05-05: 0; 2019-05-12: 0
ENGINE
CAD fixture Modification Drawing | bar: 2019-01-06 to 2019-03-17
Machine fixture | 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0
Machine engine | 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0
Hydrotesting | 2019-04-28: 0; 2019-05-05: 0; 2019-05-12: 0; 2019-05-19: 0
Static Fire Test | 2019-05-12: 0; 2019-05-19: 0; 2019-05-26: 0; 2019-06-02: 0; 2019-06-09: 0
SITE PREPARATION
Site Identification | bar: 2019-03-03 to 2019-03-24
Test Site Design | 2019-03-03: 1; 2019-03-10: 1; 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0
Coordination with Third Parties | 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0
Test Site Construction | 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0; 2019-05-05: 0; 2019-05-12: 0; 2019-05-19: 0
BASE 11 SPACE CHALLENGE
Progress Report | bar: 2019-01-06 to 2019-03-17
Static Fire Requirements Met | 2019-03-17: 1; 2019-03-24: 1; 2019-03-31: 1; 2019-04-07: 0
Static Fire Stand Design Submission | 2019-04-07: 0; 2019-04-14: 0; 2019-04-21: 0; 2019-04-28: 0
CAPSTONE CLASSWORK
ME 492 - Winter Term
PDS Report Update | bar: 2019-01-06 to 2019-02-24
Gantt Chart | bar: 2019-01-06 to 2019-02-24
Winter Progress Report Rough Draft | bar: 2019-02-17 to 2019-02-24
Winter Progress Report Final Draft | bar: 2019-02-24 to 2019-03-03
Winter Progress Report Submitted | bar: 2019-03-03 to 2019-03-10
ME 493 - Spring Term
Team Agreement
Presentation Poster
Final Report - Rough
Final Report - Final
Final Report Submitted